2005 GRN-COPP / GRN-CSO FRAMEWORK OF ENGAGEMENT IN ACTION REVIEW ROADMAP

|  |  |  |
| --- | --- | --- |
| **Timeline** | **Activity** | **Description / Outcome** |
| **PROBLEM IDENTIFICATION** |
| 2022 | The GRN COPP was dated and not implemented. It also had no implementation plan. | Strengthen **Government of the Republic of Namibia Civil Society Organizations** (GRN-CSO) partnership, a call for a review was made |
| **AGENDA SETTING** |
| 2022 | The review was proposed through the **Enhancing Participatory Democracy in Namibia** (EPDN) program with existing structures and technical and financial resources | The GRN-COPP review was identified as an activity under the EPDN Program. |
| **POLICY FORMULATION** |
| August 2022 | Stakeholder Mapping | NKE’s |
| September 2022  | Consult 4 clusters on the GRN-COPP Review | Divide the country into 4 clusters **Northern** (Omusati – Ondangwa), **Southern (**//Kharas – Keetmanshoop), **Western** (Erongo- Swakopmund) and **Eastern** (Kavango East and Zambezi Rundu and Katima Mulilo) and conduct consultations |
| November 2022 | Formulate a review report and findings | Findings pointed to formulating a Framework 2-3 years and not a policy |
| May 2023 | Present findings to the 5th Program Steering Committee meeting  | CSO’s on the steering committee were tasked to consult their constituents on the Framework of engagement for inputs.  |
| September 2023 | Anticipated feedback from CSO actors on the Framework to be presented at the 6th PSC | No formal feedback was provided by umbrellas/CSO’s on the steering committee. Civic +264 as part of its work program conducted trainings in some regions and the Framework was also presented in addition to a presentation by EPDN on the NGO day. |
| March 2024 | Second Round of stakeholder mapping | Mapping done by NPC and EPDN |
| March 2024 | Appointment of Reference Group | NPC and EPDN |
| March 2024 – May 2024 | Recruit a Non-Key Expert for the Framework Finalization | Mr. Henry Valot was consulted.  |
| 14 April - 27 April 2024 | Finalize the draft Framework by creating a costed Implementation Action Plan  | Consult the 4 clusters N, W, E and S.  |
| **POLICY ADOPTION** |
| 7 May 2024 | Present Findings to the PSC and craft way forward (PSC stands in as an inter-agency technical committee) | 22-23 May 2024 set out for National Validation of the Framework in Windhoek. |
| 8 May 2024 – 21 May 2024 | Preparations for the National Stakeholder Validation  | Ongoing |
| 22-23 May 2024 | National Stakeholder Validation Meeting | NPC and EPDN |
| June 2024 | Consolidating inputs from the validation exercise | NPC and EPDN |
| June 2024 | Presentation of the Framework to the Director General NPC through management | NPC |
| June/July 2024 | Submission to Cabinet  | NPC |
|  | Consolidate inputs from Cabinet | NPC |
| August 2024 | Launch of the Policy  | NPC and EPDN |
| September 2024 | Communication and visibility | NPC and National Structures |
| **POLICY IMPLEMENTATION, MONITORING, EVALUATION AND LEARNING** |
| September 2024 – September 2027 | Establishment of Technical Working Groups and regional support structures | National Structures |
| September 2024 – September 2027 | Quarterly and/or bi-annual policy reviews | National Structures |
| October 2027 | Framework Review National Engagement and way forward (Policy or New Framework) | National Structures |